## Purchasing REAL
Item | Purpose | Price | Product Link | Purchased? | Delivered?
Raspberry Pi 5 | SBC to collect data from SDR and magnetometer to store in the SSD | 120 | DigiKey | N | N
Heatsink + Fan | To prevent RaspPi from overheating | 9.98 | amazon | n | n
Memory Storage
SSD or SD card | To store heatmap | 21.99 | Amazon | N | N
SSD | Storage of data | 90 | Amazon | N | N
Directionality
Magnetometer | What we'll use for orientation to pair with the signal strength when processing signal | 46 | Amazon | N | N
Digital Compass + GNSS | What we'll use for orientation to pair with the signal strength when processing signal | 43 | Matek | N | N
SDR OPTIONS
USPR B210 | We chose against this one because we will only focus on 915MHz for sure and MAYBE the 2.4GHz band. The added capabilities does not justify the cost | 2387 | ettus
Lime SDR | We chose this one not only because of price but because of its compact and light footpring | 625 | limesdr
BEACON OPTIONS
LoRa Beacon | ESP32 integrated with a LoRa module. Program with Ardiuno IDE. Max TX 21dBm. REASONING: CHEAPER JUST NEED A SIGNAL TO DETECT | 19.9 | Heltec | N | N
Adafruit M0 | Microcontroller and LoRa module. Max TX | 34.95 | adafruit
Antennas
Dipole Antenna 915Mhz 3X | To transmit/recieve beacon signal. REASONING: EASIER TO CALIBRATE FOR AOA AND NO NEED TO FIDDLE WITH GROUND PLANE | 19.49 | RadioMaster | N | N
Dipole Antenna 915Mhz | To transmit/recieve beacon signal | 12.99 | pyrodrone
Quater Wave Monopole | To recieve beacon signal 4.2dBi | 7.86 | Digikey
Quater Wave Monopole | To recieve beacon signal 2.7dBi | 11.57 | Digikey
Dipole Antenna 915Mhz |  |  | GetFPV
BATTERY
Power Bank 10000mAh Portable Charger Slim External Battery Pack with 2 USB 2.4A Outputs and USB C In/Out | To power beacon. REASONING: USBC POWERBANK > LIPO FOR SAFETY | 9.99 | amazon | N | N
6s 2200 mAH LiPo | Battery to power entire system | 80 | Amazon | N | N
22,000 mAh batt pack | Battery to power entire system | 0 | Ethan's Closet | N | N
RF COMPONENTS
BP filter | Filter out noise 902 MHz to 928 MHz | 0.95 | Mouser | N | N
BP filter: ZX75BP-942-S+ Ceramic Resonator Band Pass Filter, 875 - 1010 MHz, 50Ω Connector Type: SMA | Filter out noise 875 - 1010 MHz. REASONING: MORE RELIABLE FILTERING. BUDGET ALLOWS. | 78.1 | minicircuits |  | N
BP filter: VBFZ-925-S+ Connectorized Band Pass Filter, 800-1050 MHz Connector Type: SMA | Filter out noise 800 - 1050MHz | 52.05 | minicircuits
Attenuator | Protect SDR | 0.12 | Digikey | N
Attenuator | Protect SDR -10dBi. REASONING; MORE RELIABLE ATTENUATION. BUDGET ALLOWS. | 41.62 | minicircuits
Attenuator | Protect SDR-5dBi | 13.05 | minicircuits
LNA: ZFL-1000LN+ Connectorized SMA, Low Noise, Linear Amplifier, 0.1 MHz to 1000 MHz, 50Ω Connector Type: SMA | Improve SNR | 125.17 | minicircuits
LNA: ZEL-0812LN Connectorized SMA, Low Noise, Linear Amplifier, 800 MHz to 1200 MHz, 50Ω Connector Type: SMA | Improve SNR | 375.64 | minicircuits
CONNECTORS
SMA Connector Kit | Kit for connecting all the different antennas at different configurations | 13 | Amazon | N | N
M to F SMA | To connect antennas to SDR. Also for beacon to Antenna | 18.71 | minicircuits
RP-SMA to U.FL 3X | Connection to antenna 200mm. REASONING: Cheaper and longer cable for more flexibility in mounting | 5.98 | GetFPV
RP-SMA to U.FL | Connection to antenna 152.4mm | 6.99 | DigiKey
FILAMENT
PETG SPOOL 1KG | TO SUPPORT PAYLOAD AND HOUSE BEACON | 12.79 | amazon

## Example and Template
Team Member | High level objective | Planned Duration | Planned Total Work for Week | Results and Acutal Duration | Actual Total Work for Week
Ethan Le
David Templonuevo
Team Member | Come to Team meeting with written plan for the week Clear Measureable Results - What will you get done Usually tied to WBS tasks and schedule | Break tasks down and give more detail here | Total planned work should meet your "Contract" | Come to weekly team meeting with written results What actually got done - (Measurable!) Where is the result? How long did it actually take. Sometimes actual work differs from plans (and this is ok) | Total actual work should meet your "Contract"

## Purchasing
Item | Purpose | Price | Product Link | Purchased? | Delivered?
HolyBro X500 V2 | Frame kit, flight controller, and where payload will be mounted | 795 | drUAV | N | N | Current Total | 1582.79
Spare Propellers | In case of crashing | 17 | Amazon | N | N
Jetson Nano | Single Board Computer for ML model as well as sending signals to FC for autonomous flight | 249 | Amazon | N | N
6s 2200 mAH LiPo | Battery to power entire system | 80 | Amazon | N | N
Transmitter | In case CSU Drone Center can't supply a radio transmitter | 260 | Amazon | N | N
Directional Antennae (Yagi?) | no | 32.89 | Amazon | N | N
Patch Antenna | yes | 28.97 | Mouser | N | N
BP filter | Filter out noise | 0.95 | Mouser | N | N
Attenuator | Protect SDR | 0.12 | Digikey | N | N
SSD or SD card | To store heatmap | 21.99 | Amazon | N | N
Cooling Solution for SOC?? |  |  |  | N | N
LoRa Beacon | ESP32 integrated with a LoRa module | 19.9 | Heltec | N | N
Dipole Antenna | To transmit beacon signal | 19.49 | RadioMaster | N | N
1s Lipo | To power beacon | 8.54 | Amazon | N | N
SMA F-M | Connecting and mount antennas | 2.94 | Digikey | N | N
LNA?? |  |  |  | N | N
Magnetometer | What we'll use for orientation to pair with the signal strength when processing signal | 46 | Amazon | N | N
Filament PLA+ | To house the beacon and support payload | 44.99 | Amazon | N

## 9-10-2025
Team Member | High level objective | Planned Duration | Planned Total Work for Week | Results and Acutal Duration | Actual Total Work for Week
Ethan Le | Talk to Jason and discuss ordering everything. Set up meeting with EIR. Look into a beacon for drone 2.4Ghz. | 2 hrs - Create a part list with links to everything I want. 2 hrs - Research different directional antennas and compability with SDR and desired F band | 4hr | Made preliminary parts list about items we need. Started drafting block diagram | 4hr
David Templonuevo | Attend I2P 3D printing training Start drone build plan | 1.5 hrs - Learn how to use 3d printer 3 hrs - Research drone parts and gain clearance for in-campus drone flight 2 hrs - Research how to send control signals from microcontroller to flight controller | 6.5 | x - Family Emergency on Thursday, need to reschedule I2P training 3hrs - Spoke with Drone Center about requirements based on Dr Fritz's email. Decided on securing a DIY drone 2hrs - Depending on flight controller, our SBC can use a spare telemetry port to transmit flight control signals to. | 5 hrs
Team Member | Come to Team meeting with written plan for the week Clear Measureable Results - What will you get done Usually tied to WBS tasks and schedule | Break tasks down and give more detail here | Total planned work should meet your "Contract" | Come to weekly team meeting with written results What actually got done - (Measurable!) Where is the result? How long did it actually take. Sometimes actual work differs from plans (and this is ok) | Total actual work should meet your "Contract"

## 9-17-2025
Team Member | High level objective | Planned Duration | Planned Total Work for Week | Results and Acutal Duration | Actual Total Work for Week
Ethan Le | Finish parts, meet with Jason to dicuss part compatibility, order everything after Friday meeting. Start researching algorithms and methods for source localization. | 4 Hrs Meeting with Zeta to discuss project direction. Considering directional localization for project. Confirmed the new drone specs | 4 | 1.5 hr - Met with Jason. Rescoping project to fit requirements. 2 hr - Meet with EIR to talk about project direction | 3.5
David Templonuevo | Secure funds, Continue researching drone parts, Meet with Jason, Finalize website, | 1 hr - Check in with Olivera about where the funds are 2 hrs - Meet w/ Jason on Friday, Meet w/ Matt on Monday 1 hr - Attach docs to website and upload to T drive | 4 | 1.5 hr - Meeting with Jason. Project re-scoped to shift focus away from autonomous flight. 1 hr - Uploaded index.html to senior design folder, website is up | 3.5
Team Member | Come to Team meeting with written plan for the week Clear Measureable Results - What will you get done Usually tied to WBS tasks and schedule | Break tasks down and give more detail here | Total planned work should meet your "Contract" | Come to weekly team meeting with written results What actually got done - (Measurable!) Where is the result? How long did it actually take. Sometimes actual work differs from plans (and this is ok) | Total actual work should meet your "Contract"

## 9-24-2025
Team Member | High level objective | Planned Duration | Planned Total Work for Week | Results and Acutal Duration | Actual Total Work for Week
Ethan Le | Finish Block Diagram | 1.5 - Redo RF components for AoA. Research compatitble components and connections for each to add into a visual block diagram 1.5 - Drafted a spreadsheet with all parts to send out for approval from Zeta | 3 | Meet with Zeta associates and confirmed actionable items. Meeted with Zeta in person to discuss design choices. Finished parts list and block diagram to send out. | 3
David Templonuevo | Finish Block Diagram Research modulation scheme (CSS) from beacon to SDR | 1 hr - finished block diagram flow from SDR -> Ground station 2 hr - Look into different mod schemes for LoRa -> SDR | 3 | 1.5 hrs - Had to create different options for transmitting telemetry from the Jetson to ground station 1.5 hrs - Chirp Spread Spectrum (CSS) is really the only one that makes sense for our implementation | 3
Team Member | Come to Team meeting with written plan for the week Clear Measureable Results - What will you get done Usually tied to WBS tasks and schedule | Break tasks down and give more detail here | Total planned work should meet your "Contract" | Come to weekly team meeting with written results What actually got done - (Measurable!) Where is the result? How long did it actually take. Sometimes actual work differs from plans (and this is ok) | Total actual work should meet your "Contract"
Starting next week(9/29), WWP will be update on Mondays instead of Wednesdays
This week/workload will be shorter due to this change

## 10-13-2025
Team Member | High level objective | Planned Duration | Planned Total Work for Week | Results and Acutal Duration | Actual Total Work for Week
Ethan Le | Begin purchase of components | Research and answer back to zeta e-mails, re-do purchasing list | 5 | Finalized purchasing sheet. Selected components relavent to 915MHz. Discussed with EIR and Zeta Mentors about link budget, and design choices. Communicated between project mentors to confirm the direction of our project. | 5
David Templonuevo | Begin purchase of components | Verify parts compatibility, e-mail zeta about purchasing critical components, draft testing document | 3 | Researched digital compass <-> SBC connections, it should work if we use the UARTs on the pi (3) E-mailed Zeta + EIR mentor about components that we all agree are important (1) | 4
Team Member | Come to Team meeting with written plan for the week Clear Measureable Results - What will you get done Usually tied to WBS tasks and schedule | Break tasks down and give more detail here | Total planned work should meet your "Contract" | Come to weekly team meeting with written results What actually got done - (Measurable!) Where is the result? How long did it actually take. Sometimes actual work differs from plans (and this is ok) | Total actual work should meet your "Contract"

## 10-20-2025
Team Member | High level objective | Planned Duration | Planned Total Work for Week | Results and Acutal Duration | Actual Total Work for Week
Ethan Le | Waiting for parts and meet with Zeta | 2hr - Revisitng ordering sheet and confirm funds have been transfered 2hr - Plan meetings with EiR and Zeta to discuss RF design for signal detection | 4 | Coordinated with Zeta to check in on progress. Meet with Jason and Jim to discuss project deliiverables. (1) Meet with Jim on Saturday to discuss techinical details and hardware constraints. Disussed signal detection theory, radiation theory, and revised methods due to hardware restrictions (4). | 5
David Templonuevo | Begin purchase of components | 2 - Verify parts compatibility, 1 - e-mail zeta about purchasing critical components, draft testing document 1 - Have meeting with Jim on Saturday (10/28) | 4 | Researched digital compass <-> SBC connections, it should work if we use the UARTs on the pi (3) E-mailed Zeta + EIR mentor about components that we all agree are important (1) Jim meeting (4) | 4
Team Member | Come to Team meeting with written plan for the week Clear Measureable Results - What will you get done Usually tied to WBS tasks and schedule | Break tasks down and give more detail here | Total planned work should meet your "Contract" | Come to weekly team meeting with written results What actually got done - (Measurable!) Where is the result? How long did it actually take. Sometimes actual work differs from plans (and this is ok) | Total actual work should meet your "Contract"

## 10-27-2025
Team Member | High level objective | Planned Duration | Planned Total Work for Week | Results and Acutal Duration | Actual Total Work for Week
Ethan Le | Work on DTVC doc and secure funds for purchasing | (2) Talk to Zeta, Oliveria, Hein, Chandra, and Elaine to secure funds and test equipment. Will need a Spectrum analyzer and VNA to verify signal integrity and antenna reliability (2) Work on DTVC doc | 4 | (1) Looking for Hein and Oliveria (not found). Spoke with Chandra and Elaine, found equipment and set up meeting to learn how to use equipment (2) Designed user and validation tests for proposed requirements. (1) Meet with Olivera and Hein and discussed logistics of securing funds. Got the OK to begin purchasing | 4
David Templonuevo | Work on DTVC doc and secure funds for purchasing | (2) worked on skeleton of DTVC doc, lined out sys and usr reqs (2) walked/talked w/ Ethan to help secure funds | 4 | (1) same as Ethan's above, got introduced to test eqpt by Elaine (2) Wrote cover letter and the why of the DTVC doc. Researched realistic numbers for the system reqs | 3
Team Member | Come to Team meeting with written plan for the week Clear Measureable Results - What will you get done Usually tied to WBS tasks and schedule | Break tasks down and give more detail here | Total planned work should meet your "Contract" | Come to weekly team meeting with written results What actually got done - (Measurable!) Where is the result? How long did it actually take. Sometimes actual work differs from plans (and this is ok) | Total actual work should meet your "Contract"

## 11-3-2025
Team Member | High level objective | Planned Duration | Planned Total Work for Week | Results and Acutal Duration | Actual Total Work for Week
Ethan Le | Worked on purhcasing sheet | (2) Put together initial purchasing documents for benchtop tests. Sent out form for approval and emailed Olivera about IP forms with Zeta for fund transfer | 4 | (2) Drafted purchasing document and submittted a request for parts. Briefly meet with Matt and updated him about progress. | 4
David Templonuevo | Prep for testing | (3) Research how to make the system robust to the USR1, 2, and 4 tests (1) fill out V-diagrams for the USR requirements (1) track and pick up order once it comes in | 5 | (1) Meetings with Zeta and Matt Heath (EIR Mentor) (1) Submitted DTVC docs | 2
Team Member | Come to Team meeting with written plan for the week Clear Measureable Results - What will you get done Usually tied to WBS tasks and schedule | Break tasks down and give more detail here | Total planned work should meet your "Contract" | Come to weekly team meeting with written results What actually got done - (Measurable!) Where is the result? How long did it actually take. Sometimes actual work differs from plans (and this is ok) | Total actual work should meet your "Contract"

## 11-10-2025
Team Member | High level objective | Planned Duration | Planned Total Work for Week | Results and Acutal Duration | Actual Total Work for Week
Ethan Le |  |  |  | (0.5) Meeting with Matt Heath (1) Learning how to use VNA with Chuck
David Templonuevo | Get Raspi booted and download LimeSDR Drivers | (1) Download bootloader onto the SSD (1) Download drivers from LimeSDR Documentation |  | (0.5) Meeting with Matt Heath (1) Learning how to use VNA with Chuck (2) Downloading LimeSDR Drivers to raspi, took a little longer because had to do this manually (2.5) Researched simulated signals to work on pipelining data. Talked about how to design the housing for system (distancing power supply from rf) | 6
Team Member | Come to Team meeting with written plan for the week Clear Measureable Results - What will you get done Usually tied to WBS tasks and schedule | Break tasks down and give more detail here | Total planned work should meet your "Contract" | Come to weekly team meeting with written results What actually got done - (Measurable!) Where is the result? How long did it actually take. Sometimes actual work differs from plans (and this is ok) | Total actual work should meet your "Contract"